## Guide
BOOK MARKETING PLAN - HOW TO MARKET YOUR BOOK by LYNN MORRISON
Congratulations on finishing a book! Now that the hard work of writing and editing is behind you, it's time to start planning for publication. This worksheet will help you put together your promotional plan and keep track of deadlines and deliverables along the way. If you are working with a publisher, make sure you align your plans with theirs! INSTRUCTIONS: 1. Enter the title and publication date of your book at the top of the planning worksheet 2. The monthly plan will automatically update the timeline with the correct dates 3. If you are less than six months from publication, don't stress! 4. I've shaded the timeline cells to give you a starting indication of when you might do the various activities - move these as needed! 5. Check out the activities listed for each time period, adding or removing as necessary 6. Use the additional worksheets to track the activities, including start and end dates and deliverables Need more help? Get your own copy of HOW TO MARKET YOUR BOOK on https://lynnmorrisonwriter.com/book/how-to-market-your-book/

## Plan
BOOK MARKETING PLAN - HOW TO MARKET YOUR BOOK by LYNN MORRISON
Book Title | ex. How to Market Your Book
Publication Date | 2023-08-10
| SIX MONTHS OUT | FIVE MONTHS OUT | FOUR MONTHS OUT | THREE MONTHS OUT | TWO MONTHS OUT | ONE MONTH OUT | PUB MONTH | ONE MONTH | TWO MONTHS | THREE MONTHS
| 2023-02-10 | 2023-03-10 | 2023-04-10 | 2023-05-10 | 2023-06-10 | 2023-07-10 | 2023-08-10 | 2023-09-10 | 2023-10-10 | 2023-11-10
PRE-PUBLICATION ACTIVITIES
Build your author website | bar: 2023-02-10
Create social media accounts | bar: 2023-02-10
Create social author / reader groups | bar: 2023-02-10
Create dedicated book page on website | bar: 2023-02-10
Sign up with mailing list platform | bar: 2023-02-10
Create mailing list sign-up form | bar: 2023-02-10
Add sign-up form to your website | bar: 2023-02-10
Create a freebie download to drive sign-ups | bar: 2023-03-10 to 2023-04-10
Identify similar authors and titles | bar: 2023-03-10 to 2023-04-10
Connect with authors/influencers for endorsements | bar: 2023-03-10 to 2023-04-10
Request endorsements | bar: 2023-03-10 to 2023-04-10
Reveal your cover design | bar: 2023-05-10
Recruit your promotional team | bar: 2023-05-10
Reach out to professional reviewers | bar: 2023-05-10
Distribute advance reader copies | bar: 2023-05-10
Arrange bookshop tour | bar: 2023-05-10
Arrange online tour | bar: 2023-05-10
Send out newsletters to your subscribers | bar: 2023-06-10 to 2023-07-10
Make book available for pre-sales | bar: 2023-06-10 to 2023-07-10
Set-up author accounts on Amazon, Goodreads etc | bar: 2023-06-10 to 2023-07-10
Promote book on social media | bar: 2023-06-10 to 2023-07-10
Identify opportunities for newsletter swaps | bar: 2023-06-10 to 2023-07-10
Research potential writing competitions / prizes | bar: 2023-06-10 to 2023-07-10
BOOK LAUNCH ACTIVITIES
Send out newletter announcement | bar: 2023-08-10
Post on social media | bar: 2023-08-10
Host book launch event | bar: 2023-08-10
Participate in interviews | bar: 2023-08-10
Engage with online book tour | bar: 2023-08-10
Encourage reader reviews in online stores | bar: 2023-08-10
POST-PUBLICATION ACTIVITIES
Chase up reviews with Street team | bar: 2023-09-10 to 2023-11-10
Pitch freelance articles on related topics | bar: 2023-09-10 to 2023-11-10
Attend book festivals and writing events | bar: 2023-09-10 to 2023-11-10
Use online advertising to increase sales | bar: 2023-09-10 to 2023-11-10
Submit your book for competitions | bar: 2023-09-10 to 2023-11-10
Look for holiday or seasonal hooks to promote again | bar: 2023-09-10 to 2023-11-10
Keep sending out newsletters | bar: 2023-09-10 to 2023-11-10
WRITE YOUR NEXT BOOK | bar: 2023-09-10 to 2023-11-10

## Pre-Pub
ACTIVITY | START DATE | END DATE | DELIVERABLES | COMPLETED (Y/N)
Build your author website |  |  | Website with book information (blurb, genre, pub date, etc) + author bio + contact information
Create social media accounts |  |  | Sign-up for new accounts OR update bios of existing accounts to include book information
Create social author / reader groups
Create dedicated book page on website
Sign up with mailing list platform
Create mailing list sign-up form
Add sign-up form to your website
Create a freebie download to drive sign-ups
Identify similar authors and titles
Connect with authors/influencers for endorsements
Request endorsements
Reveal your cover design
Recruit your promotional team
Reach out to professional reviewers
Distribute advance reader copies
Arrange bookshop tour
Arrange online tour
Send out newsletters to your subscribers
Make book available for pre-sales
Set-up author accounts on Amazon, Goodreads etc
Promote book on social media
Identify opportunities for newsletter swaps
Research potential writing competitions / prizes

## Launch
ACTIVITY | START DATE | END DATE | DELIVERABLES | COMPLETED (Y/N)
Send out newletter announcement |  |  | Newsletter with book cover, blurb, endorsements and links to all purchase options
Post on social media |  |  | Update cover images on all accounts to feature cover, post images/videos/text and include links on where to buy
Host book launch event
Participate in interviews
Engage with online book tour
Encourage reader reviews in online stores

## Post-pub
ACTIVITY | START DATE | END DATE | DELIVERABLES | COMPLETED (Y/N)
Chase up reviews with Street team |  |  | Check retailer / review websites to see which street team members have posted reviews. Follow-up with any who have not with a personalised, gentle reminder
Pitch freelance articles on related topics
Attend book festivals and writing events
Use online advertising to increase sales
Submit your book for competitions
Look for holiday or seasonal hooks to promote again
Keep sending out newsletters
WRITE YOUR NEXT BOOK